## Schedule
ID | Location/Activity | Scheduled Start Date | Scheduled End Date | Detected Start Date | Detected End Date
DCOP Storage Shop 1
DCOP Storage Shop 1-223A 1-223
Disk Erase Destroy 1
Disk Erase Destroy 1-511
Disk Erase Destroy 1-511
Disk Erase Material Trap 1
Disk Erase Material Trap 1-512
Disk Erase Processing 1
Disk Erase Processing 1-510
Electrical 1
Electrical 1-222
Electrical 1-222
Fire Riser and Plumbing 1
Fire Riser and Plumbing 1-210
Fire Riser and Plumbing 1-210
HWOPS Lift Assist 1
HWOPS Lift Assist 1-508
HWOPS Lift Assist 1-508
HWOPS Lift Assist 1-508
HWOPS Lift Assist 1-508
HWOPS Lift Assist 1-508
HWOPS Operating 1
HWOPS Operating 1-501
HWOPS Operating 1-501
HWOPS Operating 1-501
Huddle 1 1
Huddle 1 1-114
Huddle 1 1-114
Huddle 1 1-114
Huddle 1 1-114
Huddle 1 1-114
Huddle 2 1
Huddle 2 1-115
IDF 1
IDF 1-229A
IDF 1-229A
IDF 1-229A
Janitor 1
Janitor 1-204
Janitor 1-204
Lobby 1
Lobby 1-230
Lobby 1-230
Lobby 1-230
MDA Battery / Electrical 1
MDA Battery / Electrical 1-252
MDA Battery / Electrical 1-253
MDA Battery / Electrical 1-253
MDA Battery / Electrical 1-253
MDA Battery / Electrical 1-253
MDA Battery / Electrical 1-253
Material Search 1
Material Search 1-209
Material Search 1-209
Office 1
Office 1-202
Office 1-202
Open Office Area 1
Open Office Area 1-116
Open Office Area 1-116
Open Office Area 1-116
Open Office Area 1-116
Open Office Area 1-116
Other
Disk Erase Destroy
H1
| Install ASPs |  |  | 2025/08/06 | 2025/11/06
| Install PNMs |  |  | 2025/08/21
| Set Cooling Modules |  |  | 2025/10/15
H1A
| Install ASPs |  |  | 2025/08/06 | 2025/11/06
| Set Cooling Modules |  |  | 2025/10/25
Rack 76
POE A 1
POE A 1-251
POE A 1-251
POE A 1-251
POE A 1-251
POE A 1-251
POE B 1
POE B 1-255
POE B 1-255
Phone Room 1
Phone Room 1-108
Phone Room 1-108
Phone Room 1-108
Phone Room 1-108
Phone Room 1-108
Phone Room 1-109
Phone Room 1-109
Phone Room 1-109
Phone Room 1-109
Phone Room 1-109
RACK 11
RACK 11-12
| Set Cooling Modules |  |  | 2025/08/09 | 2025/09/13
| Install PNMs |  |  | 2025/09/06 | 2025/09/13
RACK 13
RACK 13-14
| Drill & Epoxy Anchor Bolts |  |  | 2025/08/09 | 2025/08/14
| Set Legs |  |  | 2025/08/09 | 2025/08/14
| Set Cooling Modules |  |  | 2025/08/14 | 2025/10/13
| Install PNMs |  |  | 2025/09/06 | 2025/09/13
RACK 15
RACK 15-16
| Set Cooling Modules |  |  | 2025/08/14 | 2025/08/21
| Install ASPs |  |  | 2025/08/27 | 2025/11/01
RACK 17
RACK 17-18
| Install ASPs |  |  | 2025/09/13 | 2025/11/01
| Install PNMs |  |  | 2025/09/13 | 2025/09/20
RACK 19
RACK 19-20
| Set Cooling Modules |  |  | 2025/08/21 | 2025/09/03
| Install ASPs |  |  | 2025/09/13 | 2025/11/06
| Install PNMs |  |  | 2025/09/13 | 2025/09/20
RACK 21
RACK 21-22
| Install ASPs |  |  | 2025/09/06 | 2025/11/01
| Install PNMs |  |  | 2025/09/20 | 2025/09/25
RACK 23
RACK 23-24
| Set Legs |  |  | 2025/08/21 | 2025/09/03
| Install ASPs |  |  | 2025/09/06 | 2025/10/25
| Install PNMs |  |  | 2025/09/20 | 2025/09/25
RACK 25
RACK 25-26
| Install ASPs |  |  | 2025/09/20 | 2025/10/25
| Install PNMs |  |  | 2025/09/25 | 2025/10/02
RACK 27
RACK 27-28
| Install ASPs |  |  | 2025/09/20 | 2025/10/25
| Install PNMs |  |  | 2025/09/25 | 2025/10/02
RACK 29
RACK 29-30
| Install ASPs |  |  | 2025/09/20 | 2025/11/06
| Set Cooling Modules |  |  | 2025/09/20 | 2025/10/02
RACK 3
RACK 3-4
| Install ASPs |  |  | 2025/08/14 | 2025/10/25
| Install PNMs |  |  | 2025/08/21 | 2025/08/27
RACK 31
RACK 31-32
RACK 33
RACK 33-34
| Install ASPs |  |  | 2025/09/20 | 2025/09/25
| Install PNMs |  |  | 2025/10/08 | 2025/10/13
RACK 35
RACK 35-36
RACK 37
RACK 37-38
| Set Cooling Modules |  |  | 2025/10/13 | 2025/10/22
| Install PNMs |  |  | 2025/10/15 | 2025/10/22
RACK 39
RACK 39-40
RACK 41
RACK 41-42
RACK 43
RACK 43-44
RACK 45
RACK 45-46
RACK 47
RACK 47-48
RACK 49
RACK 49-50
RACK 5
RACK 5-6
| Set Legs |  |  | 2025/07/26 | 2025/08/06
| Install ASPs |  |  | 2025/08/14 | 2025/11/01
| Install PNMs |  |  | 2025/08/27 | 2025/09/03
RACK 51
RACK 51-52
RACK 53
RACK 53-54
RACK 55
RACK 55-56
RACK 57
RACK 57-58
RACK 59
RACK 59-60
RACK 61
RACK 61-62
RACK 63
RACK 63-64
RACK 65
RACK 65-66
RACK 67
RACK 67-68
RACK 69
RACK 69-70
RACK 7
RACK 7-8
| Set Cooling Modules |  |  | 2025/07/26 | 2025/10/15
| Install ASPs |  |  | 2025/08/21 | 2025/11/01
| Install PNMs |  |  | 2025/08/27 | 2025/09/03
RACK 71
RACK 71-72
RACK 73
RACK 73-74
RACK 75
RACK 75-76
RACK 9
RACK 9-10
| Install ASPs |  |  | 2025/08/21 | 2025/11/06
| Install PNMs |  |  | 2025/08/27 | 2025/09/06
ROW 2
ROW 2-3
| Set Cooling Modules |  |  | 2025/07/26 | 2025/08/06
| Install ASPs |  |  | 2025/08/06 | 2025/10/25
| Install PNMs |  |  | 2025/08/21 | 2025/08/27
Restroom 1
Restroom 1-206
Restroom 1-206
Restroom 1-207
Restroom 1-207
SSNR and DAS 1
SSNR and DAS 1-221
Security 1
Security 1-232
Security 1-232
Security 1-232
Small meeting 1
Small meeting 1-110
Small meeting 1-110
Vestibule 1
Vestibule 1-201
Vestibule 1-201
Vestibule 1-208
Vestibule 1-208
Vestibule 1-224
Vestibule 1-224
Vestibule 1-224